## Sheet1
S No. | Screen | Change | Type | Time (h) UI | Time (h) Dev | Remarks | Asked By Ohyoon
1 | Landing | Background Image Update | New | 0.5 | 0
2 | Landing | Increase button font size | Bug | 5 | 0 | Will change all the font related issues
3 | Loader | Change loader with animation | New | 0.5 | 2.5 |  | Y
4 | Sign In Default | Bigger Font Size | Bug | 0 | 0 | Already estimated #2
5 | Sign In Default | Remake LinkedIn Button | Bug | 0.5 | 0
6 | Sign In Default | Button Positions | Bug | 0.5 | 0
7 | Sign In | Back button top left | New | 1 | 0.5
8 | Sign In | Bigger Font Size | Bug | 0 | 0 | Already estimated #2
9 | Sign In | Forget Password move in this place | New | 0.5 | 0.5
10 | Sign In Verification | New UI from Ohyoon | New | 1.5 | 1.5 |  | Y
11 | Dashboard | Textual Change Profile to Settings | New | 0 | 0 |  | Y
12 | Dashboard | Bigger Font Size | Bug | 0 | 0 | Already estimated #2
13 | Dashboard | New Pie Chart to show Actual score | New | 1 | 3 |  | Y
14 | Dashboard | Graph Update | New | 0 | 2 |  | Y
15 | Dashboard Overview | Card Proportions with respect to device size range and large icon size | New | 12 | 0 | The icon is placed as background image w.r.t category and category property and changed using class name dynamically . Hence the icon size was stategically kept small to fit in all devices. The Card size is having flexible width & fixed height inorder to show best fit in all devices w.r.t resposive grid structure. changing the height & width of the card w.r.t device size and as well as category icon size will take much effort taking care of all the cases
16 | Dashboard Overview | Notificatioin Invitation | New | 0.5 | 0 |  | Y
17 | Skills | Remove button | New | 1 | 0 |  | Y
18 | Profile | New UI from Ohyoon | New | 1.5 | 2 |  | Y
19 | Choose Player | New UI from Ohyoon | New | 1 | 1 |  | Y
20 | Game Mode | New UI from Ohyoon | New | 1 | 0 |  | Y
21 | Result Capture | New UI from Ohyoon | Bug | 3 | 0
22 | Result Capture | Textual Changes | New | 0 | 0 |  | Y
23 | Result Capture | Otther updpates | New | 0 | 1 |  | Y
24 | Result Capture | Popuo Change Text | New | 0 | 0 | Lighbox UI will not be done | Y
25 | Result Capture | Popuo Change UI | New | 4 | 2 | ALL Lighbox UI will not be done
26 | Note After Card Capture | Bigger Font Size | Bug | 0 | 0 | Already estimated #2
27 | Overview | Center alling cards | Bug | 1 | 4
28 | Overview | Change Radar Style | New | 0 | 0 | Already estimated #14
29 | Email Notifications | Change invitation | New | 0 | 2 |  | Y
|  | Total |  | 36 | 22